|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | **ANNEX 1** |  |  |  |
|  |  |  |  |  |  |
| **PROJECT PHASE** | **MILESTONE** | **DEADLINE** | **TOLLGATE** | **DATE** | **RESPONSIBLE** |
| **Phase I** | Project plan Draft |  |  | 29/03/15 | Animesh & Xavi |
| Start working on Android Assignments |  |  | 26/03/15 | Jonas, Mohammad & Thomas |
| Start working on Theory/Matlab |  |  | 26/03/15 | Animesh, Jonas & Xavi |
| Project plan Final Version |  |  | 30/03/15 | Animesh & Xavi |
|  | Final project plan submission |  | 01/04/15 | Animesh & Xavi |
|  | Reflective Diary 0 |  | 01/04/15 | Everyone Individually |
| Android Task 1 |  |  | 06/04/15 | Jonas |
| Android Task 2 |  |  | 06/04/15 | Mohammad |
| Android Task 3 |  |  | 06/04/15 | Mohammad |
| Android Task 4 |  |  | 06/04/15 | Thomas |
| Theory model & first tests in MATLAB |  |  | 08/04/15 | Animesh, Jonas & Xavi |
|  | Reflective Diary 1 |  | 15/04/15 | Everyone Individually |
|  | Progress Report 1 |  | 15/04/15 | Animesh & Xavi |
| Android Assignment Completion (All tasks) |  |  | 20/04/15 | Jonas, Mohammad & Thomas |
| Theory/Matlab work check and sync |  |  | 21/04/15 | Jonas, Xavi, Animesh |
|  | Midterm Evaluation |  | 22/04/15 | Everyone |
|  |  | Midterm Evaluation | - | Per |
|  | Reflective Diary 2 |  | 22/04/15 | Everyone |
|  | Progress Report 2 |  | 22/04/15 | Animesh & Xavi |
|  | Midterm Evaluation Follow-up 1 |  | 29/04/15 | Everyone |
|  |  | Midterm Evaluation Follow-up 1 | - | Per |
|  | Reflective Diary 3 |  | 29/04/15 | Everyone |
|  | Progress Report 3 |  | 29/04/15 | Animesh & Xavi |
| End of Phase I, Discussion and way forward |  |  | 30/04/15 | Everyone |