## Top Level
ANNEX 1
PROJECT PHASE | MILESTONE | DEADLINE | TOLLGATE | DATE | RESPONSIBLE
Phase I | Project plan Draft |  |  | 2015-03-29 | Animesh & Xavi
| Start working on Android Assignments |  |  | 2015-03-26 | Jonas, Mohammad & Thomas
| Start working on Theory/Matlab |  |  | 2015-03-26 | Animesh, Jonas & Xavi
| Project plan Final Version |  |  | 2015-03-30 | Animesh & Xavi
|  | Final project plan submission |  | 2015-04-01 | Animesh & Xavi
|  | Reflective Diary 0 |  | 2015-04-01 | Everyone Individually
| Android Task 1 |  |  | 2015-04-06 | Jonas
| Android Task 2 |  |  | 2015-04-06 | Mohammad
| Android Task 3 |  |  | 2015-04-06 | Mohammad
| Android Task 4 |  |  | 2015-04-06 | Thomas
| Theory model & first tests in MATLAB |  |  | 2015-04-08 | Animesh, Jonas & Xavi
|  | Reflective Diary 1 |  | 2015-04-15 | Everyone Individually
|  | Progress Report 1 |  | 2015-04-15 | Animesh & Xavi
| Android Assignment Completion (All tasks) |  |  | 2015-04-20 | Jonas, Mohammad & Thomas
| Theory/Matlab work check and sync |  |  | 2015-04-21 | Jonas, Xavi, Animesh
|  | Midterm Evaluation |  | 2015-04-22 | Everyone
|  |  | Midterm Evaluation | - | Per
|  | Reflective Diary 2 |  | 2015-04-22 | Everyone
|  | Progress Report 2 |  | 2015-04-22 | Animesh & Xavi
|  | Midterm Evaluation Follow-up 1 |  | 2015-04-29 | Everyone
|  |  | Midterm Evaluation Follow-up 1 | - | Per
|  | Reflective Diary 3 |  | 2015-04-29 | Everyone
|  | Progress Report 3 |  | 2015-04-29 | Animesh & Xavi
| End of Phase I, Discussion and way forward |  |  | 2015-04-30 | Everyone
Phase II | Start working on Project Report & Prototype |  |  | 2015-05-01 | As Discussed, mainly by Animesh & Xavi
|  | Midterm Evaluation Follow-up 2 |  | 2015-05-06 | Everyone
|  |  | Midterm Evaluation Follow-up 2 | - | Per
|  | Draft Project Report Integration & Protype advancement check |  | 2015-05-07 | Animesh & Xavi
|  | Reflective Diary 4 |  | 2015-05-06 | Everyone
|  | Progress Report 4 |  | 2015-05-06 | Animesh & Xavi
|  | Reflective Diary 5 |  | 2015-05-13 | Everyone
|  | Progress Report 5 |  | 2015-05-13 | Animesh & Xavi
|  | Draft Project Report Integration & Protype advancement check |  | 2015-05-14 | Animesh & Xavi
|  | Reflective Diary 6 |  | 2015-05-20 | Everyone
|  | Progress Report 6 |  | 2015-05-20 | Animesh & Xavi
|  | Progress Report 7 |  | 2015-05-27 | Animesh & Xavi
|  | Review of Final Report & Prototype |  | 2015-05-27 | Everyone
|  | Final Report & Prototype Submission |  | 2015-05-28 | Everyone
|  |  | Final Report & Prototype Submission | - | Per
2 |  | Grand Final |  | 2015-05-29 | Everyone
|  | Reflective Diary 7 |  | 2015-06-01 | Animesh & Xavi